## Slide 1
Implementing the Strategic Action Programme for THE SOUTH CHINA SEA AND GULF OF THAILAND (SCS SAP) Project
Third Meeting of the Regional Project Steering Committee (PSC)
of the SCS SAP Project
7-8 May 2025, Manila, Philippines
Report on the Findings and Recommendations of the
Mid-Term Review (MTR) of the SCS SAP Project
Peter Whalley
MTR Consultant

## Slide 2: Presentation Outline
Purpose of the MTR
Process
Initial observations
Theory of Change (ToC)
Findings
Conclusions
Recommendations

## Slide 3: Purpose of the MTR
Requirement of GEF & UNEP
To assess achievements and progress to-date
To highlight good practices and transferable lessons
To identify issues of concern and potential corrective actions
To recommend actions for the PCU, EA and IA for consideration by the PSC

## Slide 4: Process
Desk review
Brief questions to stakeholders
Mission to Thailand
  PCU
  Regional / national / local stakeholders’ meetings
  Pilot site visit – Dom Ban Bay
  Participation in regional meeting
Remote interviews
Drafting MTR report

## Slide 5: Initial observations
Project built on successful previous phase
Delay between adoption of SAP (2008) and current project
Project design was complex with 16 Outcomes and 64 outputs/indicators
3 very interlinked components supporting objective
Detailed project inception report
Delays following GEF endorsement to full project implementation - 3 PMs, COVID, change to EAs
Very slow progress reported in annual PIRs/quarterly reports specifically on the regional components

## Slide 6: Findings (1)
Project lacked an effective communication strategy
Delays implementing regional actions significantly impacts achievement of objective
Project retreat (October 2024) developed a clear and concise plan for project delivery and possible sustainability route
Emphasis on providing tools and approaches to enable COBSEA to adopt the results of the project

## Slide 7: Findings (2)
Component 1
  Progressed well in 3 countries – providing lessons for wider SAP implementation.
  Philippines pilot recently initiated – would benefit from an extension
  Indonesia and Vietnam – difficulties in initiating pilots
Component 2
  TDA/SAP (SEA:STARS) update recently started and detailed workplan developed to deliver by COBSEA 2026 IGM
Component 3
  Little progress to-date. Requires urgent attention – extension likely

## Slide 8: Theory of Change (ToC)
Components
Deliverables
Intermediate States
Impacts
C1: Reducing habitat degradation and loss via national and local reforms
C2: Strengthening knowledge-based action planning to reduce degradation of SCS
C3
Facilitating regional and national level integration
SAP pilot implementation Lessons/experiences from pilot sites provide guidance for replication and upscaling
Improved ecosystem status and services supporting sustainable livelihoods and BD goals in SCS/COBSEA region
SEA:STARS
TDA/SAP update resulting in Regional endorsement by COBSEA IGM (2026)
SEA:LEARN
Regional KM system defined/initiated
SEA:PUFFER
Regional grant and financing mechanisms agreed/initiated
Enabling Sustainable Regional Governance
Lessons from pilots utilised across SCS region via COBSEA
Updated SAP results in national implementation plans under COBSEA regional coordination
COBSEA financing improved and initiates grant facilities to enhance SAP implementation
Integrated and coordinated planning and management approaches identified for the SCS
Long-term sustainable regional coordination and governance mechanism for SAP implementation agreed

## Slide 9: Conclusions
National/local stakeholder engagement with pilots could be further developed
Whilst very delayed – the Project Retreat provided a plan that could see the project succeed with a further extension to complete
However, completion of project will require focused effort by PCU and consultants – especially for Component 3
Potential sustainability of project results through COBSEA leading to future long-term sustainable coordination of SAP implementation

## Slide 10: Actions recommended
PSC decision on pilots in Indonesia and Vietnam
PSC approves targeted project extension
PSC agrees that COBSEA is appropriate body to provide future SAP implementation coordination
PCU develop/implement Communication Strategy
PCU to initiate a SGP and identify a long-term financing mechanism to sustain SAP implementation coordination (SEA:PUFFER)
PCU to initiate small grants programme
Project transfer tools/results to COBSEA

## Slide 11: Thank you!